## Contents
Inventory & Shipment — business handoff
Katanga TVS Motor Company · written 7 October 2026 · the tables of the handoff document (Inventory_Shipment_Handoff.md)
Rows marked Unsure / Inferred / Unknown need checking in the code. The full text, the prompt-writing guide and the example prompt are in the .md file.
Sheet | What it holds | Rows
Business | Company, purchases and sales, routes, branches, currencies, team (section 1) | 28
Ports | Ports master data and their role (section 1.3) | 9
Roles | Who uses the system and what each role does (section 1.6) | 9
Glossary | Business terms and abbreviations (section 2) | 61
Menu | Menu map and known web routes (section 3.1) | 47
Flows | End-to-end flows step by step (section 3.9) | 17
Statuses | Document and object statuses with their codes (section 3.10) | 25
Movement types | Movement types, stages and their effect on containers (section 3.5) | 8
Rules | Every business rule with its status (section 4) | 69
Prompts | The prompts from the first to the latest (section 5) | 18
Scripts | SQL script numbers known (section 5.4) | 13
Next | Planned prompts in the recommended order (section 6.1) | 8
Known problems | Known problems and what to do (section 6.3) | 14
Decisions | Decisions still pending, with the options (section 6.4) | 5
Error codes | SQL error numbers and their meaning (section 7.3) | 47
Permissions | Permission codes known (section 3.8) | 14
Open questions | Everything marked unsure, and where to check | 18
| Total rows | 410

## Business
Section | Topic | Detail | Certainty
1.1 Company | Name | Katanga TVS Motor Company | Sure
1.1 Company | Activity | Distributor of TVS motorcycles in the Democratic Republic of Congo (CD), former Katanga region (Lubumbashi, Likasi, Kolwezi) | Sure
1.1 Company | Sign-in page | "Sign in to continue to Katanga TVS System"; "Katanga TVS is committed to delivering reliable, stylish and high-performance motorcycles that move lives forward." | Sure
1.1 Company | Footer | © 2026 Katanga TVS Motor Company · Powered by MAY solutions · Inspired by Mr. Issa Awada | Sure
1.1 Company | Application | Inventory & Shipment: ERP for purchasing, imports in containers, stock and costing, sales and customer payments | Sure
1.2 Buys | Main supplier | TVS Motor Company, India (supplier code SUP-0001) | Sure
1.2 Buys | Imports | By sea in containers, mostly 40HC (40 ft High Cube); one container holds a fixed number of one model (e.g. 84) = the item's Container unit | Sure
1.2 Buys | Oil | Motorcycles may travel with oil: container line "Oil included" + oil quantity per unit (information only) | Sure
1.2 Buys | Local purchases | No container: the supplier invoice is received directly, with its own charges | Sure
1.2 Sells | Customers | Sales invoices; payments collected through Receipts (cash or bank). Who the customers are (dealers, retail) is not known | Unsure
1.2 Sells | Items | Motorcycle models for sure; spare parts and oil likely | Unsure
1.2 Sells | Expiry dates | Invoice lines can carry an expiry date (lines of the same item can differ by warehouse or expiry date); how expiry is used is not known | Unsure
1.3 Routes | Typical import route | SEA Chennai → Dar es Salaam; INLAND Dar es Salaam → Kasumbalesa; CUSTOMS at Kasumbalesa; DELIVERY Kasumbalesa → Lubumbashi; offload into the warehouse | Sure
1.3 Routes | FERI | DRC imports need a FERI (electronic cargo tracking note) | Sure
1.3 Routes | Free days | The shipping line allows free days at the port; after them it charges demurrage | Sure
1.4 Branches | BR-003 | Likasi Branch, warehouse "Likasi Warehouse" (seen in PINV-BR-003-000011) | Sure
1.4 Branches | BR-002 | Another branch, probably Lubumbashi (seen in PO-BR-002-000042) | Unsure
1.4 Branches | BR-001 / head office | Existence not known | Unsure
1.4 Branches | Warehouses | Belong to a branch; a warehouse can stand under another warehouse (hierarchy, by Ali) | Sure
1.4 Branches | Offloading warehouse | A container's offloading warehouse must belong to the container's branch | Sure
1.5 Currencies | Base currency | USD; a USD document shows "Exchange Rate 1 (base currency)"; every amount also stored in base (…Base columns) | Sure
1.5 Currencies | Other currencies | Document currency with a Rate Type (e.g. "Official") and the exchange rate of the date from Master Data › Exchange Rates, editable | Sure
1.5 Currencies | CDF and others | CDF (Congolese franc) very likely defined; others not known | Unsure
1.5 Currencies | Sales invoice currency | A sales invoice can have its own currency (Ali) | Sure
1.7 Team | Bilal | Developer and contact with the business; Ubuntu, VS Code + Claude Code ("VS Code Claude"); folders ~/VSProjects/InventoryShipment-Project/Inventory_Shipment (API) and …/Inventory_Shipment.Web | Sure
1.7 Team | Ali ("AJ") | Colleague on Windows, Visual Studio + IIS Express, C:\GitProjects\Inventory_Shipment; wrote Sales / Receipts / Settings and SQL scripts 29–41 | Sure
1.7 Team | Prompt writer | Writes the business specification as prompt files (this role moves to the new session) | Sure
1.7 Team | VS Code Claude | Implements the prompts, writes the SQL from the specification, applies, tests, reports; Bilal pastes the reports back | Sure

## Ports
Code | Place | Country | Kind | Role
INMAA | Chennai | India | Sea | Port of loading for TVS
INNSA | Nhava Sheva | India | Sea
CNSHA | Shanghai | China | Sea
TZDAR | Dar es Salaam | Tanzania | Sea | Arrival port
ZADUR | Durban | South Africa | Sea | Arrival port
MZBEW | Beira | Mozambique | Sea | Arrival port
ZMKAS | Kasumbalesa | Zambia (DRC border post) | Border | Border crossing and customs
CDLUB | Lubumbashi | DR Congo | Inland | Warehouse delivery
CDKLW | Kolwezi | DR Congo | Inland

## Roles
Role | What it does (as designed) | Certainty
System administrator | System role (IsSystem = 1); user "Admin", shown "System Administrator". Holds every permission; sets up master data, users, roles, settings (email, purchase approval), document types. | Sure
Owner | Approver candidate; receives a copy of approved purchase orders (setting). No user has this role in Bilal's local database yet. | Sure
Manager | By default: view, create, confirm and offload containers; manage movements and documents; view and create container charges. Approver candidate. Test user manager1 ("Manager One"). | Sure
Purchasing / buyer | Creates purchase orders and sends them for approval. Test user buyer1. Real role name not known. | Unsure
Logistics | Plans containers (Auto-plan), types container and seal numbers, starts shipments, records movements, enters charges, attaches documents. | As designed; job title unconfirmed
Accounting | Posts supplier invoices and charges, landed cost adjustments; follows costs, stock valuation, sales profit. | As designed; job title unconfirmed
Warehouse | Offloads containers (received quantities, reason when they differ); Inventory In / Inventory Out. | As designed; job title unconfirmed
Sales / cashier | Sales invoices, receipts, customer statements, out-of-stock sales. | As designed; job title unconfirmed
(note) | Approvers are no longer taken from a role: they are ticked per user in Settings › Purchase approval. | Sure

## Glossary
Term | Category | Meaning here
PO | Documents | Purchase order; number like PO-BR-002-000042 (prefix, branch, sequence).
PINV | Documents | Purchase (supplier) invoice, PINV-BR-003-000011; the number is given at posting, a draft has none.
PRET | Documents | Purchase return, created from a posted PINV.
SINV / SRET | Documents | Sales invoice / sales return; exact codes in inventory.DocumentTypes not known; no sales-return menu seen.
Receipt | Documents | A customer payment (Sales › Receipts), with a payment method and a cash or bank account.
Exporter's Ref. | Documents | The exporter's reference; required to post an imported / shipped-in-containers invoice (65018).
Commercial invoice no. | Documents | The supplier's invoice number, typed on the PI.
Supplier reference | Documents | Free reference on the PI.
Receipt mode | Documents | On a purchase invoice: 1 = stock in when posted (local); 2 = stock in at the container offload ("Shipped in containers").
Shipped in containers | Documents | PI switch for receipt mode 2; on by default when the order has containers; locked while lines are linked (65026).
Link / Unlink (containers) | Documents | On a PI: which pieces travel in which container; each invoice line points to one container line (ContainerLineId); only before the container moves (Draft or Confirmed).
LCA | Costing | Landed Cost Adjustment (script 23): late charges on a posted local invoice; in stock → average cost, sold → COGS; refused on imported invoices (67012).
FOB | Costing | Purchase price of the goods loaded on board, before the costs of the journey; from the posted supplier invoice.
Landed cost | Costing | FOB + charges: imports = FOB per piece + posted charges on the line ÷ pieces received.
Charge | Costing | A cost of the import or purchase (freight, insurance, clearing, port fees, transport, storage, demurrage); imports on containers, local on the invoice.
Charge type | Costing | Master data (Purchase › Charge Types): default allocation method and whether the charge enters the cost.
Split rule | Costing | Dividing one charge between containers: Same (full amount each), Equal, Pieces (default), Value.
Allocation method | Costing | Dividing a container's charge over its items: Value, Quantity, Weight, Volume, Manual; cents to the largest remainders.
Charge group | Costing | Charges created together or copied share a GroupId; the provider's invoice is attached once.
Late charge / cost adjustment | Costing | A charge posted or cancelled after the offload, or on a posted local invoice; inventory.CostAdjustments (SourceKind CNTCHARGE for containers).
COGS | Costing | Cost of goods sold; sales take stock out at average cost.
Average cost | Costing | Weighted average cost per item, updated at every receipt and cost adjustment; items also keep last cost and FOB cost.
Container | Containers | A shipping container created from a purchase order; reference KTG-2026-0031 (type CNT: prefix KTG, year, 4 digits).
Container No. | Containers | The real box number, 4 letters + 7 digits (e.g. MSKU1234565); unique among open containers (69013).
Seal No. | Containers | The number of the seal closing the doors.
Container type | Containers | 20GP (inactive) and 40HC (active), with Max Weight (kg) and Max Volume (CBM); Max Units being removed (prompt 46).
Container unit | Containers | Item Definition › units: the container unit (UnitTypes.IsContainer = 1); its packing formula = pieces per container; the only source of capacity (prompt 46).
Base unit / pieces | Containers | The smallest unit (PC); container quantities are always in base units.
Auto-plan | Containers | On an approved PO: the app proposes all containers filled from the order lines; edit; create all at once (all or nothing, max 200).
Mix the rest | Containers | Auto-plan option: the rests of lines share containers; off = each rest gets its own container.
Fill % / equivalent capacity | Containers | Σ quantity ÷ pieces per container of each item (prompt 46).
Over capacity | Containers | Fill above 100%: a warning only "Load Above Capacity" can confirm (69007).
Confirm (container) | Containers | The loading plan is agreed: Draft → Confirmed.
Offload | Containers | Receiving a container's goods into stock at landed cost; reason when received ≠ loaded; re-offload tag KTG-…/2.
Close / Reopen | Containers | Close when every charge is posted (read-only); Reopen for a late charge.
Movement | Shipping | One leg of the journey, MOV-2026-000046; Planned → In progress → Completed, or Cancelled.
Stage | Shipping | What a movement type does to its containers: Origin, Sea, Transit, Port, Border, Customs, Delivery.
Start shipment | Shipping | From selected containers: one movement (default SEA) created and started at once; vessel, voyage, B/L, ETA copied.
Place of a container | Shipping | The To of its previous movement (prompt 43); never moved = its port of loading (prompt 45).
B/L | Shipping | Bill of lading; one B/L can cover several containers.
Booking No. | Shipping | The shipping line's reservation number.
ETA | Shipping | Estimated time of arrival; red "Late" badge when passed and the movement isn't completed.
Free days / last free day | Shipping | Days at the port without demurrage from the actual port arrival; red "free time over" badge after.
Demurrage | Shipping | Shipping-line fee after the free days.
Forwarder / transporter / shipping line / carrier | Shipping | Parties (Master Data › Parties) used on containers and movements.
Transshipment | Shipping | Moving a container to another vessel at an intermediate port.
FERI | Shipping | Electronic cargo tracking note required for DRC imports (a container field).
Shortage | Stock & sales | Inventory › Shortages (script 25, fn_Shortage_Live): what is missing vs what is on the way; exact formula not known.
Out-of-stock sale | Stock & sales | A sale above stock, allowed only with "Allow selling out-of-stock items"; Sales › Out-of-Stock Sales (Ali).
Date tolerance | Stock & sales | Sales-invoice rule by Ali: how far a document date may be from today (not known exactly).
Payment type | Stock & sales | On sales invoices (Ali), probably cash / credit (not known exactly).
Approver (in the app / by email) | Approval & email | Users ticked in Settings › Purchase approval; in the app = Approve / Reject; by email = personal link to the public approval page.
Requester | Approval & email | The person who sent the order for approval.
Create & send / Create & approve / Approve & post | Approval & email | Save as draft and send / approve a new order at once / approve an existing draft at once.
Send again / Withdraw | Approval & email | Resend the request with new links / take the order back to draft.
Approval link (token) | Approval & email | Personal, single use, valid N hours (default 72); opening it never decides; one click on /purchase-approval/:token.
Email outbox / Email log | Approval & email | messaging.EmailOutbox sent by a background worker; Settings › Email log (Pending / Sent / Failed).
Schema.sql | Project | Inventory_Shipment.Repository/Database/Schema.sql: every script appended in order, re-applied at every API start.
Batch | Project | A group of prompt steps: batch 8 = prompt 32, 9 = 33, 10 = 34/36, 11 = 37.
A / B steps | Project | A1, A2… run in the API project; B1, B2… in the Web project.
TEST-NN data | Project | Test data created while verifying prompt NN; VS Code Claude reports what is left.

## Menu
Area | Page | Route / note
Main | Dashboard
Inventory | Item Definition
Inventory | Price Lists
Inventory | Inventory In
Inventory | Inventory Out
Inventory | Stock Valuation
Inventory | Shortages
Purchase | Purchase Orders
Purchase | Approvals | Red count of orders waiting for me
Purchase | Purchase Invoices | /purchase/invoices/:id
Purchase | Purchase Returns
Purchase | Landed Cost Adjustments
Purchase | Charge Types
Logistics | Containers
Logistics | Movements | /logistics/movements/new, /logistics/movements/:id
Logistics | Container Charges
Logistics | Tracking
Sales | Sales Invoices
Sales | Sales Profit
Sales | Receipts
Sales | Customer Statement
Sales | Out-of-Stock Sales
Backoffice › Master Data | Branches / Sites
Backoffice › Master Data | Warehouses
Backoffice › Master Data | Currencies
Backoffice › Master Data | Exchange Rates
Backoffice › Master Data | Item Families
Backoffice › Master Data | Brands
Backoffice › Master Data | Parties
Backoffice › Master Data | Unit Types
Backoffice › Master Data | Container Types | /setup/master-data/container-types
Backoffice › Master Data | Ports
Backoffice › Master Data | Attachment Types
Backoffice › Master Data | Movement Types
Backoffice › Master Data | Payment Methods
Backoffice › Master Data | Cash / Bank Accounts
Backoffice › Users & Permissions | Users
Backoffice › Users & Permissions | Roles
Backoffice › Users & Permissions | Role Permissions
Backoffice › Users & Permissions | Permissions
Backoffice › Users & Permissions | Login audit
Configuration | Document Types
Configuration › Settings | General | Ali's global settings (e.g. Allow selling out-of-stock items)
Configuration › Settings | Email | /configuration/email
Configuration › Settings | Email log
Configuration › Settings | Purchase approval
Public | Approval page | /purchase-approval/:token (no sign-in)

## Flows
Flow | Step | Action | Detail
A. Import | 1 | PO draft | Created by a buyer: supplier, branch, currency, lines with warehouse, quantity, unit price, discount %.
A. Import | 2 | Approval | Create & send / Send for approval (status 5, locked); approvers in the app and/or by email; Approved = posted (number, supplier email with PO-{number}.xlsx, copies, requester told); Rejected = back to draft with reason; under the limit or approval off = posted directly.
A. Import | 3 | Containers | Auto-plan or Add Container; container numbers and seals; confirm.
A. Import | 4 | Supplier invoice(s) | From the containers, one per item, or invoice first then add / link containers; Exporter's Ref. required; post: no stock yet.
A. Import | 5 | Shipment | Start shipment (SEA Chennai → Dar es Salaam), then INLAND → Kasumbalesa, CUSTOMS, DELIVERY → Lubumbashi; each movement started and completed.
A. Import | 6 | Charges and documents | Freight, clearing, transport, port fees, demurrage on containers; split, allocated, posted; documents attached (B/L, packing list, FERI).
A. Import | 7 | Offload | At the warehouse: stock in at landed cost; average cost updated.
A. Import | 8 | Close / late charges | Close the container; a late charge: reopen, post, cost adjusted (in stock → average cost, sold → COGS).
A. Import | 9 | Sale | Sales invoice: stock out at average cost → COGS → Sales Profit.
A. Import | 10 | Receipt | Customer payment; Customer Statement updates.
B. Local purchase | 1 | PO and approval | As in A.
B. Local purchase | 2 | Create Invoice | From the PO, one per item, "Shipped in containers" off.
B. Local purchase | 3 | Charges and post | The invoice's own charges; post: stock in at FOB + charges (receipt mode 1).
B. Local purchase | 4 | Late charges | LCA (later "+ Add charge" on the posted invoice, prompt 38).
B. Local purchase | 5 | Return | PRET from the posted invoice.
C. Sale and payment | 1 | Sales invoice | Currency, payment type, client address, date tolerance; out-of-stock only if allowed (Ali, details unknown).
C. Sale and payment | 2 | Receipt | Customer payment, customer statement, sales profit (Ali, details unknown).

## Statuses
Object | Code | Status | Note | Certainty
Purchase documents (PO, PINV, PRET) | 1 | Draft |  | Sure
Purchase documents (PO, PINV, PRET) | 2 | Posted | For a PO = approved | Sure
Purchase documents (PO, PINV, PRET) | 3 | Cancelled |  | Sure
Purchase documents (PO, PINV, PRET) | 4 | Closed | A PO auto-closes when fully invoiced, or is closed by hand | Sure
Purchase documents (PO, PINV, PRET) | 5 | Waiting for approval | PO only, locked | Sure
Containers | 1 | Draft | Created from a PO (Add Container or Auto-plan) | Sure
Containers | 2 | Confirmed | Confirm, or automatically when a shipment starts | Sure
Containers | 3 | In Transit | Sea / transshipment / inland / border movement started, or Dispatch Date typed | Inferred
Containers | 4 | At Port | Sea movement completed or port arrival started, or Actual Port Arrival typed | Sure
Containers | 5 | Cleared | Customs completed or delivery started, or Customs Release Date typed | Sure
Containers | 6 | Offloaded | Offload | Sure
Containers | 7 | Closed | Close after the offload | Sure
Containers | 8 | Cancelled | Cancel with a reason | Sure
Movements | 1 | Planned |  | Sure
Movements | 2 | In progress | Start | Sure
Movements | 3 | Completed | Complete | Sure
Movements | 4 | Cancelled | Cancel with a reason | Inferred
Container charges | 1 | Draft | Can be changed or deleted | Sure
Container charges | 2 | Posted | Locked; enters the cost | Sure
Container charges | 3 | Cancelled | With a reason | Sure
Emails (outbox) |  | Pending | Waiting to be sent (sending off keeps them Pending) | Sure
Emails (outbox) |  | Sent |  | Sure
Emails (outbox) |  | Failed | After at most 5 attempts, with a readable error | Sure
Approval history events |  | Sent for approval · Sent again · Reminder sent · Approved (in the app / by email) · Approved directly · Rejected · Withdrawn · Posted without approval · Sent to the supplier · Not sent to the supplier |  | Sure
Invoice line ↔ container |  | Linked / Not linked | "Not linked" is only a warning on shipped-in-containers invoices | Sure

## Movement types
Code | Movement | Stage | Effect on the containers
LOAD | Loading at supplier | Origin | No status change.
SEA | Sea freight | Sea | Started: In Transit (dispatch date). Completed: At Port (actual port arrival).
TRANSHIP | Transshipment | Transit | Started: In Transit.
PORT | Port arrival | Port | Started: At Port.
INLAND | Inland transport | Transit | Started: In Transit (a container already At Port stays At Port).
BORDER | Border crossing | Border | Started: In Transit; sets the border crossing date.
CUSTOMS | Customs clearance | Customs | Completed: Cleared (customs release date).
DELIVERY | Warehouse delivery | Delivery | Started: Cleared.

## Rules
Area | Rule | Status | Reference / note
Numbering | Numbers are defined per document type in Configuration › Document Types (NumberPrefix, NumberPerBranch, YearInNumber, NumberLength, NumberOnPost). | Implemented
Numbering | Purchase documents: prefix + branch + sequence (PO-BR-002-000042, PINV-BR-003-000011); number assigned at posting (PO when approved / posted); drafts have no number. | Implemented | PRET pattern unsure
Numbering | Containers KTG-YYYY-NNNN (type CNT); container box number unique among open containers (69013); re-offload ledger number KTG-…/2. | Implemented
Numbering | Movements MOV-YYYY-NNNNNN, assigned at the first save. | Implemented
Numbering | Scripts Database/NN_Module_Description.sql and prompts docs/prompts/NN-title.md have separate numbers; pull before numbering (Ali writes scripts too). | Convention
Purchase | A PO is a draft until posted; posting a PO = approving it; the PO auto-closes (4) when fully invoiced. | Implemented
Purchase | An invoice made from a PO takes its supplier and branch; each line at most what remains on its source line. | Implemented
Purchase | One item per supplier invoice: several lines of one item allowed, never two items; one draft per item from Create Invoice / from Containers / import; refusal 65029; Split by item; Post selected. | Implemented | Prompt 37, script 44
Purchase | Imported invoice: Exporter's Ref. required to post (65018); no own charges (65020); no LCA (67012). | Implemented
Purchase | A PI can be created directly from an order that has containers (refusal 65021 removed). | Implemented | Prompt 41, script 43
Purchase | "Shipped in containers" (receipt mode 2): default on when the order has containers; no stock at posting; locked while linked (65026). | Implemented | Script 43
Purchase | Link / Unlink on a PI: draft or posted PI; containers Draft or Confirmed only (65027); linking splits the line; a PI not from a PO cannot have containers; a container line is never invoiced twice. | Implemented | Script 43
Purchase | Add container / Auto-plan from the PI: on the PI's order, linked at once, PI's item only. | Implemented | Script 43
Purchase | Containers card on every PI with reasons for disabled buttons; "Turn it on" for drafts; quantity ≤ min(not in a container, order lines allow); order approved or closed; no orange warning when not shipped in containers. | Decided – prompt 44
Purchase | "+ Add charge" in every status: local draft = invoice charges; local posted = late charge → Post late charges (LCA); imported = container charge dialog. | Decided – prompt 38
Purchase | One purchase-order page from everywhere; buttons visible but disabled with a tooltip (draft, waiting, closed, cancelled); hidden only without permission. | Decided – prompt 39
Purchase | Purchase returns from a posted PINV. | Implemented | Detailed rules unsure
Purchase | Discount % per purchase line. | Implemented | Sales discounts: Ali
Approval | Approvers chosen per user (In the app / By email); purchase.orders.approve has no effect. | Implemented | Script 42 + prompt 36
Approval | Approval needed when the setting is on and the total in base currency is above the limit (0 = every order); otherwise Post ("Posted without approval"). | Implemented
Approval | Rights checked in SQL at decision time, whatever the channel. | Implemented
Approval | "The person who sends an order may approve it" (default on); off → creator / requester can't approve (65023) nor receive the request. | Implemented
Approval | Approve & post / Create & approve for an in-app approver ("Approved directly"). | Implemented
Approval | Links personal, single use, 72 h default (1–720); one decision closes all links; opening a link never decides (one click on /purchase-approval/:token). | Implemented
Approval | Reminders every N hours (default 24, 0 = never, max 168) with new links; Withdraw; Send again. | Implemented
Approval | After approval: supplier email with PO-{number}.xlsx (setting), copies to Owner role and typed addresses, requester told; no supplier address → warning + Send to supplier…. | Implemented
Approval | After rejection: requester told; draft shows "Rejected by {name} on {date}: {reason}". | Implemented
Approval | 65016 only while "Email the approved order to the supplier" is on; withdraw reason stored; create-and-approve warnings; Approve confirmation. | Decided – prompt 42
Email | One sender mailbox (Settings › Email); password encrypted (Data Protection, App_Data/keys), never returned or logged; Gmail needs an app password; the system mailbox is inventory.shipment.2026@gmail.com. | Implemented | Prompt 36
Email | Every email is sent from that mailbox; suppliers and approvers only receive; replies and bounces come back to it. | Implemented
Email | "Send emails" off = Pending in the Email log; on = worker every 30 s, 10 at a time, max 5 attempts; test email works while off. | Implemented
Email | Links use "Address of the application" (else App:PublicBaseUrl); localhost links work only on the PC running the app. | Implemented | Production URL needed
Containers | Created only from an approved and open PO (status 2); lines of other approved POs can be added. | Implemented
Containers | Quantities in pieces; loadable = ordered − invoiced without container − loaded elsewhere (69008). | Implemented
Containers | Status only moves forward (Cancel Offload and Reopen go back on purpose). | Implemented
Containers | Free days: last free day = actual port arrival + free days; red badge after. | Implemented
Containers | Offload needs: confirmed; every line invoiced by posted invoices (69016); no movement in progress; warehouse of the branch; received ≤ loaded; reason when different. | Implemented
Containers | Offload effects: landed cost = FOB + posted charges ÷ received; charges frozen; average / last / FOB costs updated. | Implemented
Containers | Cancel Offload refused after a cost adjustment (69018) or when the stock is gone. | Implemented
Containers | Close when every charge is posted; Reopen for late charges; delete drafts only. | Implemented
Containers | Auto-plan: whole containers per line first, rest packed (first fit, largest first, fill to the brim when fewer containers), Mix the rest, max 200, all or nothing. | Implemented | Script 28
Containers | Capacity today: typed pieces → item Container unit → container type Max Units; over capacity warning 69007 (Load Above Capacity). | Implemented | To be replaced by prompt 46
Containers | Capacity from one source: the item's Container unit; fill % = Σ qty ÷ pcs per container; no Container unit → "—", no warning, Auto-plan refuses; Max Units removed (columns kept); Max Weight / Volume stay. | Decided – prompt 46
Movements | Planned → In progress → Completed; Cancelled; one movement in progress per container (70012). | Implemented
Movements | Start shipment: default SEA between the containers' common ports; drafts confirmed; Plan only option; vessel / voyage / B/L / ETA copied. | Implemented | Script 28
Movements | Place rule: only containers at the From (= To of their previous movement); Save refuses others (70015); Start refuses while the previous movement is not completed (70016); planning ahead allowed. | Implemented | Prompt 43; check the error numbers
Movements | Never-moved containers are at their port of loading (or on an Origin movement ending there); no port of loading → any From with a note; Origin movements only take never-moved containers. | Decided – prompt 45 | Not explicitly confirmed by Bilal
Movements | The Containers card is the list with checkboxes; reloads on From change; no Add containers dialog; Save needs ≥ 1; Start / Complete disabled with unsaved changes; Start re-checks in SQL. | Decided – prompt 45
Movements | Excel / paste import: number then ref, capitals / spaces / dashes ignored, never creates containers, max 500, results per number. | Implemented | Prompt 43 (basic)
Movements | Import validation: only valid numbers can be ticked; Download the result (Result + Summary); template served from public/templates. | Decided – prompt 45
Costing | Weighted average cost per item (plus last and FOB cost); sales at average cost (COGS). | Implemented
Costing | Import landed cost = FOB per piece + posted charges on the line ÷ pieces received; estimate before offload. | Implemented
Costing | Charges Draft → Posted → Cancelled; only posted charges that enter the cost count; rate of the charge date (editable). | Implemented
Costing | Split: Same / Equal / Pieces (default) / Value; allocation: Value / Quantity / Weight / Volume / Manual; cents to largest remainders. | Implemented
Costing | Copy a charge to other containers: drafts of the same group; refused if the container already has it. | Implemented
Costing | Late charge after offload → cost adjustment (in stock → average cost, sold → COGS); offload no longer reversible. | Implemented
Costing | Local purchases: invoice charges while draft; LCA after posting (67011 must be posted; 67012 not on imported). | Implemented
Attachments | Containers: type, date, note; general or linked to a movement / charge; one upload → several containers. | Implemented
Attachments | Every document: type required and filtered per document; never required to post; old files "Other"; one shared dialog; no direct upload; 20 MB everywhere. | Decided – prompt 40 | Updated 4 Oct
Inventory & sales | Allow selling out-of-stock items + Out-of-Stock Sales page. | Ali – details unknown
Inventory & sales | Sales invoice: own currency, client address, date tolerance, payment type. | Ali – details unknown
Inventory & sales | Customer receipts with payment methods and cash / bank accounts. | Ali – details unknown
Inventory & sales | Warehouse hierarchy; import of documents whatever the warehouse; no Expiry Date in the import template. | Ali
Inventory & sales | Price lists: per document type DefaultPricing / PriceEditable. | Unsure | Check the code
Dates | Timestamps in *Utc columns; dates without time have no time zone. | Implemented
Dates | API sends *Utc with "Z"; the web shows local time once. | Decided – prompt 42
Security | Permissions per role; administrator has all; Manager defaults; sensitive new permissions admin-only. | Implemented
Security | Links never decide on GET; tokens never in logs or responses; SMTP password never returned. | Implemented
Security | Concurrency with RowVersion: "This … was modified by another user. Reload the page and try again." (409). | Implemented

## Prompts
Prompt | Title / what it does | Status | Notes
1–29 | Earlier prompts (titles not known to this session) | Unknown | Files should be in docs/prompts of the API repository; scripts 23–26 came from that period
30 | Approval UI / email outbox worker for script 26 | Replaced | Replaced by prompt 36 ("Do not run prompt 30")
31 | Not known | Unknown
32 | Batch 8 — Containers at the centre (script 27): containers from the PO, invoices from containers, movements, charges, documents, tracking | Done | A1–A4, B1–B5
33 | Batch 9 — Many containers per order (script 28): Auto-plan, bulk actions, Start shipment for chosen containers, charge copy, Create & send | Done | Except approval steps A4 / B3 (replaced by 36)
34 | Batch 10 — Purchase approval: who approves, email settings, the cycle | Partly done | A1 became script 42 (not 29); A2–B3 replaced by 36
35 | Fix "The request field is required." on PINV / PRET save and post | Unknown | Probably done or not needed; test by saving a draft PRET
36 | Batch 10 final — Email and approval layer (A1–A3, B1–B4) | Done | Leftovers → prompt 42
37 | Batch 11 — One item per supplier invoice (script 44, 65029) | Done | Verified 2 Oct; ran after 41
38 | Charges on a purchase invoice, draft or posted ("+ Add charge") | Not started
39 | One purchase-order page from everywhere; disabled buttons with reasons | Not started
40 | Attachment types on every document | Not started | Updated 4 Oct: one dialog, no direct upload, 20 MB
41 | Containers from the purchase invoice (script 43) | Done | Ran before 37
42 | Approval follow-ups after 36 | Not started | "Prompt 42" ≠ "script 42"
43 | Movement: containers with checkboxes, Excel list, place rule | Done | Partly superseded by 45
44 | Create containers from a purchase invoice: check, then fix with every validation | Not started | Status unknown; the reported problem was explained (invoices 1227, 1322)
45 | Movement: one list with checkboxes following the From; Save / Start guards; never-moved rule; validated import; result download; template | Not started
46 | Container capacity from the item's Container unit; Max Units removed | Not started

## Scripts
Script | Content | Prompt / origin
23 | Landed Cost Adjustment (LCA) of posted local invoices | Before this session
24 | First containers module ("batch 6") | Before this session
25 | Shortages + item Container unit | Before this session
26 | Purchase-order approval by email, email outbox | Before this session (UI: prompt 30, replaced by 36)
27 | Container-centric model | Prompt 32
28 | Bulk containers, Start shipment, charge copy, approvers | Prompt 33
29 (mine) | Standalone approval / email script — NOT used | Delivered, rejected in favour of 42
29–41 | Ali's scripts (sales, receipts, settings, out-of-stock sales, warehouses, import…) | Ali
42 | Approval and email settings | Prompt 34 A1
43 | Invoice containers | Prompt 41
44 | One item per supplier invoice | Prompt 37
45 (probably) | Movement container picker and place rule | Prompt 43 — check
next | Free numbers for prompts 42, 44, 45, 46 (and 38 / 40 if they need SQL) | Pull before numbering

## Next
Priority | Prompt | What it does | Before running
1 | 45 | Movement list with checkboxes, Save / Start guards, validated import | Save Movement_Containers_Import_Template.xlsx in the Web's public/templates/ first
2 | 46 | Capacity from the item's Container unit only | Fix TEST38-A Container unit (1 → 120) or let the Check list it
3 | 44 | PI Containers card with reasons and all validations | Give VS Code invoices 1227 and 1322 when it asks
4 | 40 | Attachment types everywhere, one upload dialog | Bilal asked again on 4 Oct
5 | 42 | Approval follow-ups (UTC Z, 65016, withdraw reason, Approve confirmation) | Sending is already on; test-email cleaning may find nothing
6 | 38 | "+ Add charge" on posted invoices
7 | 39 | One purchase-order page | Optionally add the Create Invoice preview count fix
if needed | 35 | Request-field fix | Only if never run: save a draft PRET to test

## Known problems
Problem | What to do
Stale API after new code (404 / 405, "Not found") | fuser -k 7089/tcp 5174/tcp, then npm run dev in Inventory_Shipment.Web (dev.mjs reuses a running API).
API start fails with SQL 18456 (login failed) | The connection string lacks Bilal's sa password (appsettings.json may hold AJ's / a placeholder after merge ff3f905); fix: line 2 of ~/.bashrc export ConnectionStrings__<Key>=…Password=$SQLCMDPASSWORD…; key name to confirm; whether applied is unknown.
Ali's PC: DLLs locked by IIS Express, port 5174 busy | Stop IIS Express / the old Vite before npm run dev.
GitHub copies may be behind GitLab | GitLab origin is the team repo; GitHub (bfa-14/…) changes only with git push github main.
Uncommitted work (prompts 36 rest, 41, 37, then 43…) | Commit by feature; never commit appsettings.Development.json, App_Data/, screenshots; git pull --no-rebase; push.
Test data in Bilal's database | Orders 1136–1146, KTG-2026-0022, PO-BR-002-000048, PINV-BR-002-000033, KTG-2026-0031..0033, TEST41-A stock, MOV-2026-000046.
Invoices 1076 and 1078 (posted, mode 2) have pieces outside containers | Link them or cancel them.
Item TEST38-A Container unit = 1 | Set it to 120 in Item Definition.
Test users with @example.com emails bounce | Use real addresses or Gmail + aliases.
Email links point to localhost:5174 | Only work on Bilal's PC; set the real address in production.
Owner role has no users | No Owner copies are sent.
Ali's database after pulling | Gets scripts 42+ at API start; his POs then need approval (Settings › Purchase approval).
tools/check-repo.sh missing | tools/refresh-dbproject.sh stops at it; offered to write it.
Containers User Guide outdated | Chapters 5, 7, 8 after prompts 37, 41, 43–46.

## Decisions
Decision | Options considered | Current default
Never-moved containers on a movement | (a) any From (prompt 43); (b) port of loading, or an Origin movement ending at it; (c) port of loading only | (b) in prompt 45 — stated twice, not confirmed
Container units per container type | (a) one Container unit per item; (b) container unit types linked to container types | (a) for now; (b) only if 20GP comes back
Create Invoice preview count with existing drafts | (a) leave it (result is right); (b) API preview excluding drafts (in prompt 39) | Undecided
Script numbering with Ali | (a) pull before numbering and tell each other; (b) number ranges per person | (a) advised
Production email and links | Keep the Gmail account (app password) or a company mailbox (Microsoft 365 / Workspace); real application URL | Not discussed

## Error codes
Number | Module | Meaning
65000 | Purchase | Validation
65004 | Purchase | Changed by another user (concurrency)
65006 | Purchase | Not found
65008 / 65009 | Purchase | Exist; meaning not known here
65010 | Purchase | Not a draft
65013 | Purchase | The order needs approval
65014 | Purchase | Approval link not usable (says why)
65015 | Purchase | Nobody can approve
65016 | Purchase | Supplier has no email (to change with prompt 42)
65017 | Purchase | Not allowed to approve
65018 | Purchase | Exporter's reference required
65019 | Purchase | Container line mismatch / exceeded
65020 | Purchase | Charges belong to the containers
65021 | Purchase | Order shipped in containers (refusal removed by prompt 41)
65022 | Purchase | Approval not needed
65023 | Purchase | Self-approval refused
65024 | Purchase | Approval settings
65025 | Purchase | Email settings
65026 | Purchase | "Shipped in containers" locked while linked
65027 | Purchase | Container already moving
65028 | Purchase | Invoice can't be linked
65029 | Purchase | One item per supplier invoice
65030+ | Purchase | Expected next free (prompt 44)
67011 | Landed cost adjustment | The invoice must be posted
67012 | Landed cost adjustment | Refused on an imported invoice
69000 | Containers | Validation
69005 | Containers | Not editable
69006 | Containers | Not found
69007 | Containers | Over capacity (warning, confirmable)
69008 | Containers | More than the order line still allows
69009 | Containers | Nothing to create
69013 | Containers | Container number already used
69016 | Containers | Not fully invoiced (offload)
69017 | Containers | Container line already invoiced
69018 | Containers | Cost adjustments exist (offload not reversible)
70000 | Logistics | Validation
70001 | Logistics | Duplicate (container already has this charge)
70004 | Logistics | Concurrency
70005 | Logistics | Not editable
70006 | Logistics | Not found
70010 | Logistics | Invalid status
70012 | Logistics | Container travelling with another movement
70013 | Logistics | Allocation data missing
70014 | Logistics | In use
70015 | Logistics | Container not at the movement's From (prompt 43)
70016 | Logistics | Previous movement not completed (prompt 43)
HTTP | All | Validation → 400, not found → 404, the rest → 409, with the SQL message

## Permissions
Code | Sort order | What it allows
containers.movements.manage | 1410 | Manage Shipment Movements: plan, start, complete, cancel movements; Start shipment
containers.charges.view | 1420 | View Container Charges
containers.charges.create | 1430 | Create Container Charges (enter, edit, delete, copy drafts)
containers.charges.post | 1440 | Post Container Charges
containers.charges.cancel | 1450 | Cancel Container Charges
containers.attachments.manage | 1460 | Manage Container Documents
masterdata.movementtypes.manage | 1470 | Manage movement types
containers.overcapacity |  | Load Above Capacity
(container permissions, codes not listed here) |  | View / Create / Confirm / Offload / Cancel / Close / Delete Containers
purchase.orders.approve |  | Now "(not used)": approvers are chosen in Settings › Purchase approval
purchase.orders.post |  | Post purchase orders; Send again, Withdraw, Send to supplier
purchase.approval.manage |  | Manage Purchase Approval Settings (administrators by default)
settings.email.manage |  | Manage Email Settings (administrators by default)
messaging.emails.view | 920 | View the Email log

## Open questions
Topic | What is unsure | Where to check
Customers | Who they are (dealers, retail) | Ask Bilal
Items | Spare parts and oil besides motorcycles | Item Definition data
Expiry dates | How expiry dates on invoice lines are used | Purchase lines code, Ali's import
Branches | Name of BR-002; existence of BR-001 / head office | Master Data › Branches
Currencies | Which currencies besides USD (CDF?) | Master Data › Currencies
Roles | Real role names (buyer etc.) | security.Roles
Sales documents | SINV / SRET codes; whether sales returns exist | inventory.DocumentTypes
Shortage | The exact formula | fn_Shortage_Live (script 25)
Date tolerance | The exact rule | Ali's sales-invoice scripts / commits
Payment type | The values (cash / credit?) | Ali's commits
Price lists | How DefaultPricing / PriceEditable choose prices | Document types + Price Lists code
Sales Profit | How it is computed | Ali's code
Numbering | LCA and sales number formats; PRET pattern | inventory.DocumentTypes
Status codes | Container status 3 and movement status 4 (inferred) | logistics procedures
Permissions | Codes of the basic container permissions | security.Permissions
Prompts 1–31 | Titles and contents | docs/prompts in the API repository
Prompt 35 / 44 | Whether they were run | Ask Bilal / git log
Connection string fix | Whether the env-var fix for 18456 was applied | Ask Bilal